## Gantt Chart
PROJECT
ML 24/25-09 Semantic Similarity Analysis of Textual Data
Project Start: |  |  | 2025-01-01
TASK | TASK DESCRIPTION | PROGRESS | START | END
Title | ML 24/25-09 Semantic Similarity Analysis of Textual Data |  | 2025-01-01 | 2025-03-25
Sprint 1 | Gathering information, analyzing the project, and reviewing current methods. |  | 2025-01-01 | 2025-01-14 | Achieved
Sprint 2 | Project Kickoff |  | 2025-01-15 | 2025-01-28 | Achieved
Sprint 3 | Project testing and deployment |  | 2025-01-29 | 2025-02-11 | Not completed in this sprint
Sprint 4 | Final Testing and bugs removal |  | 2025-02-12 | 2025-03-25
Sprint 5 | Completion of Documentation |  | 2025-02-26 | 2025-03-11
Sprint 6 | Finalization of the Project |  | 2025-03-12 | 2025-03-25